## Slide 1
PROJECT DEVELOPMENT PLAN
CabalMesh
Roadmap, milestones & execution plan
AUG 2026 → JAN 2027
Scoped against a code-level status audit rather than the pitch. Five phases, each with a stated constraint and an falsifiable exit condition.
kurodenjiro · Baseline: docs/product-status.md

## Slide 2
ROADMAP
02
ROADMAP
Aug 2026 → Jan 2027
AUG
SEP
OCT
NOV
DEC
JAN
01
Recovery & intent parsing
02
Hardware concepts & demand
03
Marketplace goes live
04
Verification & negotiation
05
Confidential compute
Phases overlap deliberately. Bars are execution windows, not commitments — each phase exits on its condition, not its date.

## Slide 3
ROADMAP
03
ROADMAP
Five phases
01
Recovery guarantees & intent parsing
Eliminate unrecoverable key loss; restore NL intent parsing over the existing validated draft pipeline.
Aug – Sep 2026
02
Hardware concepts & demand signal
Two reference designs, published as concepts. Waitlist volume decides whether tooling is worth funding.
Sep – Oct 2026
03
Marketplace goes live
Convert verified relay work into on-chain rewards and open a market for node modules.
Oct – Nov 2026
04
Verification & bounded negotiation
Close the gap between claimed and enforced: real circuit verification, guardrails in Rust.
Nov – Dec 2026
05
Confidential compute & platform parity
Scope FHE/MPC for negotiation privacy; close the desktop keystore and BLE-plane gaps.
Dec 2026 – Jan 2027

## Slide 4
PHASE 1
04
01
PHASE 1 · AUG – SEP 2026
Recovery guarantees & intent parsing
Today a wiped device means permanently lost funds. Guardian recovery and passphrase unlock already ship; this phase closes the remaining gaps and reconnects the intent parser.
RECOVERY
24–48h delay on guardian recovery with a veto notification, so a compromised device can be countermanded
6-digit PIN unlock, gated on the platform keystore's hardware-enforced retry counter (ticket 21)
Guardian enrollment and share-distribution UI, matching the shipped protocol
Guardian storage inherits the SECURITY passphrase setting rather than staying file-key-protected
INTENT PARSING
Editable chip UI, so a mis-parse is corrected in place instead of falling back to the form
parse_intent_chat QA — the parser already emits the validated fields New.tsx consumes
Conversational recovery assistant for the device-loss path, where static UI branches badly
Invariant held: the model emits IntentFields only; Rust validates, previews and signs
Exit condition
A wiped device reconstructs its key from 3-of-5 guardians with the veto window verified on physical hardware, and a natural-language intent reaches broadcast without widening what Rust will sign.

## Slide 5
PHASE 2
05
02
PHASE 2 · SEP – OCT 2026
Hardware concepts & demand signal
Two reference designs that make the protocol legible — and a demand test before committing capital to tooling.
MESH · MODEL · PROVER
ShadowBox
One node instead of three: mesh relay, local model and prover in a single fanless slab, with RADIO / CRYPTO / POWER bays mirroring the in-app module system.
PHYSICAL ESCROW
The Nobody Box
A parcel locker whose bolt turns on the on-chain release. A load cell reports that something went in and something left — never what it was.
Deliverable is industrial design and a demand signal, not units. No manufacturer is engaged; tooling spend is gated on waitlist conversion.
Exit condition: both designs rendered, waitlist live, and signup volume sufficient to justify — or kill — the hardware track.

## Slide 6
GO-TO-MARKET
06
GO-TO-MARKET
Distribution is continuous, sequenced behind shipped capability
Each push is anchored to a milestone that gives the audience something verifiable. No campaign runs ahead of the artifact it describes.
AUG – SEP
BUILD IN PUBLIC
⌁ Recovery ships
Engineering updates on the offline settlement path — the one differentiated capability that already works end to end. Zero cost, compounding audience.
Follower growth, update engagement
SEP – OCT
CONCEPT REVEAL
⌁ Renders complete
Publish both reference designs. Waitlist is instrumented as a demand test — no pre-orders taken, no delivery implied.
Waitlist conversion rate
OCT – NOV
PRIMARY LAUNCH
⌁ Marketplace live
The substantive launch, once relay rewards and modules are transactable. Kaito mindshare campaign and mesh missions activate here.
Active relaying nodes, missions completed
DEC – JAN
TECHNICAL PROOF
⌁ Verification real
Credibility content once circuit verification is genuinely running. Targets developer and press audiences, not retail.
Press pickups, developer signups
Audience: Avalanche ecosystem builders · privacy and secure-hardware communities · off-grid and censorship-resistant trade
No paid acquisition until organic conversion is demonstrated at the Oct–Nov launch. Hardware remains concept-only pending a manufacturing partner.

## Slide 7
GO-TO-MARKET
07
GO-TO-MARKET · CHANNELS
Mesh missions & the Kaito mindshare campaign
Two tracks, deliberately asymmetric: product missions settle on-chain, social missions are scored off it. Rewards weight toward verifiable usage.
PRODUCT MISSIONS
Settled against on-chain state
1
Broadcast an intent over the mesh with no network path available
2
Relay a threshold volume of gateway traffic
3
Enroll guardians and complete a recovery dry run
4
Acquire or equip a module NFT once the Marketplace ships
SOCIAL MISSIONS · KAITO
Scored by Kaito's mindshare model
5
List CabalMesh as a Kaito Genesis/Yapper project
6
Publish about the protocol — Kaito scores and ranks the post publicly
7
Referral that converts to a completed product mission, not a bare signup
REWARD MECHANIC
Threshold completion mints a soulbound Genesis Node badge via the existing CabalMeshVoucher contract — reusing the non-transferable primitive already backing the in-app Standing Badge. Kaito determines rank; on-chain state determines eligibility. Nothing is gated on a metric Kaito cannot verify.

## Slide 8
PHASE 3
08
03
PHASE 3 · OCT – NOV 2026
Marketplace goes live
Marketplace.sol and CabalMeshVoucher.sol are deployed to Fuji but unreachable from the app. This phase makes relay work economically real.
Relay traffic
Earn MB
Convert to AVAX
Acquire module
Higher yield
A reflexive loop: utilisation raises module value, which raises the incentive to relay.
SCOPE
— Redeploy CabalMeshVoucher with mint authority bound to RelayRewards — closing the current unrestricted-mint path
— Wire gateway relay to RelayRewards.recordGatewayRelay, paid atomically from the settlement it carries
— Ship MARKET and VAULT → MODULES against the redeployed contracts; compute yield from verified ownership, not local state
Exit condition: MB earned from attributable gateway relay converts to AVAX and buys a module whose yield effect is verifiable on-chain.

## Slide 9
PHASE 4
09
04
PHASE 4 · NOV – DEC 2026
Verification & bounded negotiation
The deck currently claims verified proofs and negotiating agents. Neither is enforced today. This phase makes the claims true or removes them.
CURRENT STATE
— No ZK proving code at all — the unused Noir stub was deleted rather than left to imply a capability
— No agent-to-agent negotiation — matching resolves against a fixed listing price
— No structural bound preventing an unsafe negotiation implementation
TARGET STATE
✓ Proof verification runs against a real Noir circuit in CI, not a non-empty-input check
✓ Bounded offer / counter-offer / accept protocol with a hard round limit
✓ Price guardrails enforced in Rust — the model proposes, it never sets the bound
Constraint: no nargo in the current CI image. Negotiation is sequenced behind single-shot matching reliability — llama2 JSON adherence is already marginal, and multi-turn compounds it.

## Slide 10
PHASE 5
10
PHASE 5 · DEC 2026 – JAN 2027 · EXPLORATORY
ZK proves the outcome.
It does not hide the negotiation.
Genuinely open research. The deliverable is a scoped feasibility assessment, not shipped code.
Assess FHE and MPC for negotiation-content privacy — no prior art exists in this codebase
Bind the desktop vault key to Secure Enclave / TPM instead of the current 0o600 file provider
Resolve the BLE plane on Windows and Linux, where backend::choose returns None and the app degrades silently

## Slide 11
Revised against the code, not the narrative.
Every claim in this deck is traceable to a file in the repository. When the status audit changes, this plan changes with it.
Current phase
Recovery & intent parsing
Source & docs
github.com — CabalMesh
Deployed
Avalanche Fuji Testnet
CABALMESH · PROJECT DEVELOPMENT PLAN