## Slide 1
CABALMESH
PROJECT PLAN · ONE PAGE
ONE TRUE STORY, THEN THE NETWORK AROUND IT
Six months, five phases,
one dependency chain.
Every phase is scoped from what the code does today, and sequenced so each one unblocks the next. Windows are planned execution ranges: phase N+1 starts when phase N’s definition of done is met, not on a calendar trigger.
HORIZON
Aug 2026 → Jan 2027
OWNER
kurodenjiro
BASELINE
product-status.md
REVISED
2026-08-19
BASELINE — READ OUT OF THE CODE, NOT THE PITCH
WORKS END TO END
Mesh — libp2p, mDNS, gossipsub
BLE offline plane — iOS, Android
Intent lifecycle, compose to proof
Escrow live on Avalanche Fuji
Offline signing + relay queue
Vault — AES-256-GCM
Guardian mesh unlock
UI EXISTS, BEHAVIOUR DOES NOT
PRIVACY — parsed, no routing code
MODE — labels, no strategy differs
SWAP / STAKE — every path is Escrow
USDC · WETH · BTC.b — never funded
NOT WIRED UP AT ALL
AI negotiation — called nowhere
Marketplace — contracts inert
ZK — no proving code in the build
FHE / MPC — no code exists
Recovery delay + veto
Mobile PIN — blocked on ticket 21
TIMELINE
AUG 26
SEP
OCT
NOV
DEC
JAN 27
01
Identity, recovery & AI intent parsing
02
Marketing, sales & hardware devices
03
Marketplace goes live
04
Harden verification & negotiation
05
Confidential compute & platform hardening
PHASES — GOAL AND DEFINITION OF DONE
01
Identity, recovery & AI intent parsing
AUG – SEP 2026
IN PROGRESS
Close the lose-the-device risk; turn typed language back into a validated intent draft.
DONE WHEN — A wiped device restores from 3-of-5 guardians with a live 24h veto window on real hardware, and a typed intent parses into editable chips.
02
Marketing, sales & hardware devices
SEP – OCT 2026
NEXT
ShadowBox and the Nobody Box as concept products, plus a pre-order channel. Marketing/BD, not firmware.
DONE WHEN — Both devices have finished renders, a pre-order page is live, and one campaign reaches beyond current testers.
03
Marketplace goes live
OCT – NOV 2026
NEXT
Relay traffic → MB → AVAX → modules → higher relay yield. Fix mintVoucher access control first.
DONE WHEN — A user earns MB from real gateway relaying, converts it to AVAX, and equips a module that visibly changes relay yield on HOME.
04
Harden verification & negotiation
NOV – DEC 2026
LATER
Make the ZK and AI claims true end to end: write the circuit and the proving path, and enforce guardrails in Rust.
DONE WHEN — A bid’s proof is generated and verified against a real circuit from a command the app calls; two agents complete a bounded negotiation without breaching a guardrail.
05
Confidential compute & platform hardening
DEC 2026 – JAN 2027
EXPLORATORY
FHE/MPC feasibility, desktop key store, and the Windows/Linux BLE decision.
DONE WHEN — A feasibility write-up and a scoped follow-on plan for FHE/MPC — not shipped code.
RISKS & BLOCKERS
NEXT 30 / 60 / 90
No physical iOS/Android test device
P1
Borrow test hardware before Phase 1 is called done.
Native key-store plugin (ticket 21)
P1
Own workstream; a PIN needs a hardware retry counter.
No manufacturing partner
P2
Phase 2 runs as marketing/BD; renders do not need it.
Voucher redeploy is one-way
P3
Explicit go/no-go. Testnet, no value locked today.
No ZK code, no nargo in CI
P4
The unused stub was deleted; budget Phase 4 to write the circuit, not wire one.
30 DAYS
— 24h recovery delay + veto notification
— Scope ticket 21 as its own workstream
— Hide SWAP / STAKE and unfunded assets
60 DAYS
— Ship editable chips, QA the chat-intent flow
— Recovery assistant for lost devices
— Finish renders, draft landing-page copy
90 DAYS
— Launch pre-order page + first campaign
— Run mesh missions, mint Genesis badges
— Draft the voucher redeploy go/no-go
FULL PLAN — docs/pitch/CabalMesh-Project-Plan.md · AUDIT — docs/product-status.md · github.com/kurodenjiro/Cabal-Mesh
A LIVING PLAN. WHEN THE AUDIT CHANGES, THE PLAN IS WHAT GETS REVISED.